## Risk Matrix
Risk ID | Clause | Finding | Likelihood | Impact | Risk Score | Risk Level | Recommended Control | Owner | Status
R1 | 5.2 | Undocumented ISMS Policy | 4 | 5 |  |  | Develop ISMS policy | Management | Open
R2 | 5.2 | No compliance commitment | 4 | 4 |  |  | Include compliance commitments | Management | Open
R3 | 5.2 | Outdated policy | 3 | 4 |  |  | Periodic review policy | Management | Open
R4 | 6.1 | No risk assessment process | 5 | 5 |  |  | Implement risk framework | Security Team | Open
R5 | 6.1 | Outdated risk register | 4 | 5 |  |  | Update risk register | Security Team | Open
R6 | 6.1 | No Statement of Applicability | 4 | 4 |  |  | Create SoA | Security Team | Open
R7 | 9.2 | No audit program | 5 | 5 |  |  | Develop audit program | Audit Team | Open
R8 | 9.2 | Audits not conducted | 4 | 5 |  |  | Schedule audits | Audit Team | Open
R9 | 9.2 | No audit evidence | 4 | 4 |  |  | Maintain audit records | Audit Team | Open